## Roadmap Overview
Roadmap Overview
1 Jan 2026 - 31 Dec 2026 | Phase 2 (6 - 18 months]
Assess and Implement tactical remediations
2025Q3-2026Q1 | Perform gap analysis on IRB models (Including distressed restructures)
Estimation of MoC where necessary and compile roll-out plans
2026Q2 | Submit roll-out plans to the PA
2026Q3 | Bilateral engagements and feedback from PA
2026Q4 | Finalisation and implementation of MoCs
1 Jan 2027 - 31 Dec 2028 | Phase 3 (18 - 42 months]
Execution of roll-out plans related to Basel III post-crisis reforms
1 Jan 2027 | Reporting on distressed restructures
1 Jan 2029 - 31 Dec 2030 | Phase 4 (42 - 66 months]
Execution of roll-out plans related to distressed restructures
Additional notes
Tier | Plan | Associated submission requirements
Tier1 | Fully decommission only/ change in model scope/ add floors only | CRO letter Summary information
Tier2 | Recalibrate Should the update to the model result in a material impact, the model change must be considered as a tier 3 model change. | CRO Letter Summary information Validation Report Minutes and presentations of approval committee(s)
Tier3 | Update (same methodology) Should the update to the model not result in a material impact, the model change must be considered as a tier 2 model change. | For material impact models (refer par. 2.1.2 D2/2014): CRO Letter Summary information Development documentation Validation documentation Minutes and presentations of approval committee(s) Model code and masked data
Tier4 | Redevelopment | CRO Letter Summary information Development documentation Validation documentation Minutes and presentations of approval committee(s) Model code and masked data

## Roadmap 1
Bank Name:
A) High Level Exposure Information
Approach | Current Credit Exposure | Proposed Credit Exposure
AIRB
FIRB
STA
B) High Level Models Information
Number of models
Retail
Wholesale
C) Description of materiality classifications
Materiality Classification | Discription
D) Additional notes
Tier | Plan | Associated submission requirements
Tier1 | Fully decommission only/ change in model scope/ add floors only | CRO letter Summary information
Tier2 | Recalibrate | CRO Letter Summary information Validation Report Minutes and presentations of approval committee(s)
Tier3 | Update (same methodology) | For material impact models (refer par. 2.1.2 D2/2014): CRO Letter Summary information Development documentation Validation documentation Minutes and presentations of approval committee(s) Model code and masked data For non-material models revert to Tier2 requirements
Tier4 | Redevelopment | CRO Letter Summary information Development documentation Validation documentation Minutes and presentations of approval committee(s) Model code and masked data

## Roadmap 2
E) Model Inventory with Model Change Roll-out Plan
Model Name | Unique code | Model Type | Materiality classification | Compliant with revised Regulations | Compliant with revised directive on distressed restructures | Tier | Description of Plan | MoC Required | Bank portfolios (Asset class) Proportion of total exposure | Exposure | Current EAD | Current RWA | Current Capital | Revised Regulations MoC estimate | Revised directive on distressed restructures MoC estimate | Proposed RWA | Proposed Capital | Revised Regulations Planned Submission Date | Comply with revised distressed restructure directive in Phase 4 | Revised credit restructure directive Planned Submission Date
|  | EAD |  | No | No | Tier1 |  | No | [10 empty] | No
Note on D3: Bank defined materiality classification, as described in sheet Roadmap 1
Note on E3: Is model fully compliant with Basel III reforms?
Note on F3: Is model fully compliant with revised credit restructures directive?
Note on H3: Description of model gap and rework required.
Note on I3: Does the model require an MoC for the revised Regulations and/or revised credit restructures directive? It the answer is No, substantiate this in the associated MoC column.
Note on J3: Provide all the portfolios that make use of the model, together with the associated asset class the portfolio is reported under and the proportion of the portfolio relative to the total exposure the model is used to assess.
Note on O3: Provide the value of the MoC to be applied, also describing how the estimate was obtained.
Note on P3: Provide the value of the MoC to be applied, also describing how the estimate was obtained.
Note on T3: Does the bank require the use of phase 4 for the revised credit restructures directive model changes?

## Phase 3&4 Submission Info
Summary Information Required for Model Change Submissions
1 | Bank name
2 | Submission date
3 | Material or non-material change
4 | Rating system | Name: Unique number: Type (PD, LGD, EAD):
5 | Reason(s) for change(s), particularly if the current rating system has a specific deficiency as opposed to requiring refinement
6 | Brief description of changes
7 | Portfolio(s)/business units covered by the rating system
8 | Regulatory asset class(es) affected by the rating system | Complete the following measures for each regulatory asset class affected by the rating system: Regulatory asset class Exposure Rxxx (date) Current EAD Rxxx (date) Current RWA Rxxx (date)
9 | Qualitative factors considered in assessment of materiality
10 | Relevant committee approval Committee: | Committee: Date:
11 | Proposed implementation date for rating system changes
12 | Supporting documentation for material changes | Development documentation Validation documentation Documentation presented to approval committee Approval committee minutes Model code and masked data
13 | Proposed rating system complies with the minimum requirements as specified in regulation 23(13)(b) of the Regulations | Yes/no
14 | If stated No in item 13: detail the reasons for non-compliance, including actions to address non-compliance

## Lookup (hidden)
Binary | Type of model | Tier
Yes | PD | Tier1
No | EAD | Tier2
| LGD | Tier3
Tier4